## Sheet1
Note: Only contains the most notable or most recent bugs. I forgot to make note of a lot of smaller ones that arose in the middle of developing features. The table provides the title or name of a bug, what happened, whether it was resolved and if there was a resolution for this bug.
Bug Title | Bug Description | Resolved? | Resolution
Animation 1st Frame Desync | Some animations on the RPG and Defibrilator will play before the character's animator plays the animation. | Not Resolved - Source and solution unknown | N/A
Equipment Charge - Ammo - 1 | Weapons with eqipment charges could reach -1 ammo or further. | Resolved | Restricted reloads of weapons with Equipment Charges, can only reload when charges are greater than zero. Equipment charges are consumed when weapons are fired and not when they are reloaded.
VFX Play On Spawn | VFX created using the VFX Graph always play when they are spawned. | Resolved | Explosion code was always running at start.
Constant Health Regen Loop | After taking damage, health would regenerate as expected. When reaching max health, health would regenerate to max and then would subtract the same damage healed in the next tick. | Resolved | Only run damage code when delta health < 0
Player damageable when dead | Players could still be hit after dying, meaning the death particles would play again and more death trophies would spawn | Resolved | I lost my notes on this one. I think it wasn’t setting something correctly.
Projectiles all moved to first hit point | When firing multiple projectiles, they would all move to the point that the first projectile hit. | Resolved | Implemented active projectile array that is linked directly to raycast command index instead of all projectile array.
Projectiles phase through objects | Projectiles would move through objects that are in their direct path. | Resolved | Projectiles were ticking multiple times due to not being correctly terminated. Resolved when projectile hashing and single array was implemented
Projectiles hit owner | Projectiles would get stuck on the owner of the projectile, causing self damage. | Resolved | Implemented ignored colliders and multiple raycast hits in new projectile simulation
Defibrilator no ammo consumed | Defibrilator would not consume ammo when used. | Resolved | Attempting to "fire" the defibrilator will always consume ammo regardless of whether it hits or not.
Defibrilator enemy revives | Defibrilator can revive enemies when hitting their trophies instead. | Resolved | Defibrilator checks trophy at point of trying to revive rather than relying on cached isFriendly value.
Carriable Rotation Zero | When carriable rotation has not been assigned/modified, carriables do not rotate at all. | Resolved | Initialised Grab Rotation Offset with Quaternion.Identity
Interactable Event Always Triggers | Interactables always invoke their events, even when the user releases the interaction key early. | Resolved | Only invokes interactable events when the interaction is completed
Defibrillator non-functional | The Defibrillator currently cannot revive anybody. | Not Resolved - Source and solution unknown | N/A
Performance Drop on First RPG Shot | When firing the RPG for the first time, it causes huge stutters on all clients. Could be related to object pooling? | Not Resolved - Source and solution unknown | N/A